## Schedule
Apr 4-6, 2013 |  | 2013 National Contest & Academy in Fort Wayne, IN | Grand Wayne Convention Center 120 Jefferson Blvd. Fort Wayne, IN
Tuesday, April 2 ver 021213
Board and Staff arrive
Wednesday, April 3
|  | Set up Dairy Challenge Central office | Dairy Challenge Central, Jefferson B | DCC: Solid square of four 4 ft to 8 ft tables. Three 8 foot tables along the walls. Electrical outlets for 4 to 6 lap top computers, plus one for the copier. 8 chairs. We will need 2 keys for this room. Also, we will need a high speed copier placed in the room for the duration of our contest. We will have our own set of keys for the IT and DCC office
|  | Set up IT office | IT, Board Room | IT: 2-8' tables pushed together to make solid square with 6 chairs, access electrical outlets. We will need 2 keys for this room.
Coaches, teams, board, staff arrive in Ft. Wayne
4:00-7:00 PM |  | Computer check-in for early arriving teams | IT, Board Room
1:00-5:00 PM |  | NAIDC Board of Directors meeting | Hilton, Hamilton Hall | Board room set for 20. break service
18:30 |  | NAIDC Board of Directors dinner | off site? | Dinner for up to 25, board plus key host comm mbrs
Thursday, April 4
8:00-5:00 PM |  | Computer check-in | Board Room
Each team should check in laptops and USB drive by 5 PM. Must provide user names and passwords for each computer.
9:00 AM - 9:30 AM |  | Registration (Academy participants) | Anthony Wayne Ballroom Foyer
10:00 AM–12:00 PM |  | Pre-Tour Seminar (teams and Academy students) | Anthony Wayne Ballroom AB | banquet seating for 350, 35 rounds of 10, stage, podium, mic, large screen, av cart with electrical access ADD: Count may be closer to 250. Head table for 6 with 6 wireless mics on table stands
12:30-3:30 PM |  | Lunch & Farm Tour (teams and Academy students) | lunch at farm | Schools are responsible for their own transportation
5:00–5:30 PM |  | Registration (Contest Coaches, Judges, Sponsors/Volunteers) | Anthony Wayne Ballroom Foyer | Four 6 to 8 ft check in tables with chairs: two pushed together for student registration, one for judges registration, and one for volunteer registration. Access to electrical. Dropping in house phone
20:00 |  | Distribution of computers and contest materials. All teams should be present. | Anthony Wayne Ballroom AB; CONTEST STUDENTS | 32 rounders with 6 chairs each. Podium and mic, table for materials to side of podium. Additional 5 tables with chairs set along perimeter (somewhat removed from the 32) plus 4 - 8' tables to turn computers back in with 2 chairs at each near entrance to main hallway. May need to drop electrical from ceiling. Tall sign holders on each table FACEBOOK STATIONS: set up 3 high tops Thur and Sat (not Friday). We'll place laptops. Need 1 section of pipe and drape as backdrop and to hang banner. Access to internet and electrical to all 3. ADD tall table stantions numbered 1-32 to designate table assignments. REMOVE electrical after Thur night. Keep wall open between A&B to allow tables to spill into A
19:00 |  | Academy Advisor orientation | Calhoun Ballroom AB
20:00 |  | Judges’ orientation | Jefferson C | 6 rounders with 8 chairs each. We supply powercord and strip to 4 of the tables.
20:00 |  | Academy Session 1: Distribution of case study materials | Calhoun Ballroom AB | 20 rounders of 10 (13+2 extra) for 160 students plus 40 volunteers No need for electrical at the tables. Small riser up front? Screen, electrical, AV cart, microphone
22:00 |  | Data computers checked back in | Anthony Wayne Ballroom AB | Same location as distribution, or at IT if nearby
Friday, April 5
6:00–7:00 AM |  | Sponsor and media check-in | Dairy Challenge Central, Jefferson B
6:00–7:00 AM |  | Team Breakfast buffet | Anthony Wayne Ballroom AB | banquet seating for 250, rounds of 10, podium, mic, large screen, av cart with electrical access. Buffets will likely be set in prefunction area. Have area for 1st bfast.
6:30–6:45 AM |  | Contest overview and instructions for contestants and judges | Anthony Wayne Ballroom AB
6:30 |  | Volunteer meeting (instructions for farm visits) | Jefferson A | Theater seating for 50 , head table for 4 OR can do one set for weekend: 10 rounders of 8
6:45–7:00 AM |  | Judges meeting | Jefferson C | Existing set
8:00 AM-9:00 AM |  | Academy Breakfast buffet | Anthony Wayne Ballroom AB | Existing set - another 150-200 eaters - Changed time to flow into their 9 am session. Will have area for 2nd bfast
7:10 |  | Teams begin loading buses for contest dairy visits. | Hilton Lobby entry
Judge panels follow buses travelling in a group in their own vehicle.
7:20 |  | Bus 1 leaves for contest dairy 1 | Hilton Lobby entry
7:30 |  | Bus 2 leaves for contest dairy 2 | Hilton Lobby entry
7:40 |  | Bus 3 leaves for contest dairy 3 | Hilton Lobby entry
7:45 |  | Bus 4 leaves for contest dairy 4 | Hilton Lobby entry
8:15–8:30 AM |  | Teams and judges arrive at dairies | Contest dairies
8:30 AM–10:30 AM |  | Coaches meet with Board of Directors | Jefferson A | existing set; may add podium, screen, av cart with electrical access
8:45 |  | Dairy managers welcome teams, provide overview and guidelines | Contest dairies
9:00–11:00 AM |  | On-site assessment of contest dairies | Contest dairies
9:00-12:00 Noon |  | Academy Session 2: Analyzing a Dairy (BREAKOUTS IN 4 SEPARATE ROOMS) | Calhoun A | In each room: 6 rounders of 10 (5 +1 extra) , podium, mic, screen, av cart with electrical access
Calhoun B
Calhoun CD
The Gallery
11:00–11:15 AM |  | All teams gather with dairy managers for group interview with judges observing | Contest dairies
11:30 |  | Teams and judges depart dairies; boxed lunches served on busses
11:30 AM–5:00 PM |  | Coaches and media eat lunch and visit contest dairies | Contest dairies
Coaches will visit their contest dairy for 2 hours and then another dairy for 1 hour.
12:00-1:00 PM |  | Academy: Luncheon | Anthony Wayne Ballroom AB | existing set - anticipate 200
12:30 |  | Teams arrive at Hotel | Hilton Lobby entry
12:30 |  | Teams pick up data computers and work room assignments | IT, Board Room | existing set
12:30–1:00 PM |  | Judges have lunch with dairy managers | Jefferson C | existing set, lunch for up to 30. 5 rounders of 6
12:45–5:45 PM |  | Teams plan and develop presentations in assigned work rooms | Hilton
1:30-5:00 PM |  | Academy Session 3: Farm Visit | Hilton Lobby entry | use morning buses, have industry reps go with students to farms, observe and teach along the way. Students need to go to farm not being used by their school
1:00–1:15 PM |  | Judges meeting, instructions for the afternoon | Jefferson C | Existing set
1:00–1:15 PM |  | Volunteer meeting, instructions for interviews | Jefferson A | Existing set
2:00–4:00 PM |  | Individual team interviews with dairy managers with judges observing (12 minutes/team) | Dairy A: Harrison Meeting Room A | Theater seating for 25 , head table for 4. Signage indicating Dairy #
Dairy B: Harrison Meeting Room B
Dairy C: Harrison Meeting Room C
Dairy D: Harrison Meeting Room D
2:00–5:00 PM |  | Snacks available | Harrison Lobby | May do 2 ice cream stations, 1 near interview rooms and 1 near hotel work rooms
2:00–5:00 PM |  | Sponsor booth set-up | Anthony Wayne Ballroom AB | As many as 20 draped 8' tables lining the perimeter of the room, access to electrical. Set up 15. no charge to plug into the wall.
17:00 |  | Academy students return from farms
18:00 |  | Judges turn in their assessment and contest data | Dairy Challenge Central, Jefferson B | Dairy Challenge Central
6:00–6:35 PM |  | Teams turn in final presentations and return computers | IT, Board Room | IT Room
6:00–7:00 PM |  | Industry Social | Anthony Wayne Ballroom AB | May do additional bar in lobby area if needed.
7:00–10:00 PM |  | Friday dinner and program (teams and Academy students) | Anthony Wayne Ballroom AB | 36-40 rounds of 10 covered, small stage with podium, AV screen, projector cart, access to electrical at cart with 2 plugs for computer & lcd, dance floor - yet to determine entertainment for evening (ask KIM)
Saturday, April 6
6:15–9:00 AM |  | Breakfast buffet | Anthony Wayne Ballroom AB | Existing set
6:30–8:30 AM |  | Sponsor set-up for Career & Innovation Fair | Anthony Wayne Ballroom AB | Existing set
6:45 |  | First morning presentation teams arrive at assigned prep rooms | Prep rooms | table for 4, access to electrical. NAIDC will place a computer and projector. Don't need screens. Signage indicating Dairy#
|  | Computers will be preloaded with their presentations. Teams prep for 1 hour. Teams must turn in financial materials at the start of prep time. | Dairy A: Hilton Foster Room | see set above - asked about setting up rooms on Fri nite
|  |  | Dairy B: Hilton Farnsworth Room | see set above
|  |  | Dairy C: Hilton Nuckols Room | see set above
|  |  | Dairy D: GWCC Gallery Room | see set above
7:00–7:35 AM |  | Judges meeting | Harrison A
Instructions for the day
7:00 |  | Volunteer meeting | Jefferson A
Instructions for morning volunteers
7:45–11:45 AM |  | Morning team presentations (60-minutes intervals) | Presentation rooms | Presentation Room Set: theater seating for 50 at back podium at left front wall with 4 chairs to the side, av table with electrical access, screen at front, judges table at center facing podium with seating for 5. water station. Coffee/water placed at judges' table in each presentation room. SET THE NIGHT BEFORE
|  | Team presentation – 20 minutes | Dairy A: Harrison Meeting Room A | see set above - asked about setting up rooms on Fri nite
|  | Judges’ questions – 10 minutes | Dairy B: Harrison Meeting Room B | see set above
|  | Judges’ deliberation – 15 minutes | Dairy C: Harrison Meeting Room C | see set above
|  | Judges’ feedback – 10 minutes | Dairy D: Harrison Meeting Room D | see set above
Immediately after presentations and questions, teams are photographed with coaches.
Teams are debriefed after judges’ feedback.
|  | After debriefing, teams are escorted to the career fair, which is mandatory. | Debriefing room for all dairies: Harrison E | Debriefing room set: Set 4 tables for 6 with tall signs (Dairy A , Dairy B, Dairy C, Dairy D) SET THE NIGHT BEFORE
8:00 AM-12:00 PM |  | Academy Session 5A: Farm Analysis Presentations for Dairies A&B | Dairy A - Calhoun A | Set both rooms with 6 rounders of 10 (5 tables of 8 + 2 Academy Adv/table) + addt table for coaches? AV NEEDS??
Dairy B - Calhoun B
8:00-10:00 AM |  | Career & Innovation Fair - Dairy C Contest Teams and Academy students | Anthony Wayne Ballroom AB | 32 contest kids and 40 academy kids = 72 participants/farm
|  | Afternoon Contest and Academy presentation teams are required to attend. |  | As many as 20 draped 8' tables lining the perimeter of the A side of room, access to electrical.
8:00-10:00 AM |  | Corporate Technology Presentations - Dairy D Contest Teams and Academy students | Jefferson A and Jefferson C
Afternoon Contest and Academy presentation teams are required to attend.
| CHOOSE | 8:00-Talk A | Jefferson A | 9 rounders of 8 (72 total) + additional chairs for coaches?? Add podium/mic?
| ONE: | 8:00-Talk E | Jefferson C | 6 rounders of 8 (existing set). Add podium/mic?
| CHOOSE | 8:30-Talk B | Jefferson A
| ONE: | 8:30-Talk F | Jefferson C
|  | 9:00-Talk C | Jefferson A
|  | 9:30-Talk D | Jefferson A
10:00 AM–12:00 PM |  | Career & Innovation Fair - Dairy D Contest Teams and Academy students | Anthony Wayne Ballroom AB | existing set
Afternoon Contest and Academy presentation teams are required to attend.
10:00 AM–12:00 PM |  | Corporate Technology Presentations - Dairy C Contest Teams and Academy students | Jefferson A and Jefferson C | existing sets
Afternoon Contest and Academy presentation teams are required to attend.
| CHOOSE | 10:00-Talk C | Jefferson A
| ONE: | 10:00-Talk E | Jefferson C
| CHOOSE | 10:30-Talk D | Jefferson A
| ONE: | 10:30-Talk F | Jefferson C
|  | 11:00-Talk A | Jefferson A
|  | 11:30-Talk B | Jefferson A
10:00 AM - 2:00 PM |  | Team photos - Schools should report for their team photo at their discretion during this time block
11:00 AM–1:00 PM |  | Lunch buffet | Anthony Wayne Ballroom AB | flow of approx 400
11:30 |  | First afternoon presentation teams arrive at assigned prep rooms | Prep rooms | existing sets
|  | Computers will be preloaded with their presentations. Teams prep for 1 hour. Teams must turn in financial materials at the start of prep time. | Dairy A: Hilton Foster Room
Dairy B: Hilton Farnsworth Room
Dairy C: Hilton Nuckols Room
Dairy D: GWCC Gallery Room
11:45 AM–12:30 PM |  | Judges’ lunch | Anthony Wayne Ballroom AB | set reserved signs on 2 tables of 10 for judges at entrance
12:05 |  | Volunteer meeting | Jefferson A
Instructions for afternoon volunteers
12:30–4:30 PM |  | Afternoon team presentations (60-minutes intervals) | Presentation rooms | existing sets
|  | Team presentation – 20 minutes | Dairy A: Harrison Meeting Room A
|  | Judges’ questions – 10 minutes | Dairy B: Harrison Meeting Room B
|  | Judges’ deliberation – 15 minutes | Dairy C: Harrison Meeting Room C
|  | Judges’ feedback – 10 minutes | Dairy D: Harrison Meeting Room D
|  | Teams are debriefed after judges’ feedback. | Debriefing room for all dairies: Harrison E | 4 tables of 6 in the room
After debriefing, teams are escorted to the career fair, which is mandatory.
1:00-5:00 PM |  | Academy Session 5B: Farm Analysis Presentations for Dairies C&D | Dairy C - Calhoun A | each room set with 12 rounders of 10 (10+2 addtl for coaches?) AV needs??
Dairy D - Calhoun B
1:00–3:00 PM |  | Career & Innovation Fair - Dairy A Contest Teams and Academy students | Anthony Wayne Ballroom AB | existing set
Morning Contest and Academy presentation teams are required to attend.
1:00-3:00 PM |  | Corporate Technology Presentations - Dairy B Contest Teams and Academy students | Jefferson A and Jefferson C | existing sets
Morning Contest and Academy presentation teams are required to attend.
|  | 1:00-Talk A | Jefferson A
|  | 1:30-Talk B | Jefferson A
| CHOOSE | 2:00-Talk C | Jefferson A
| ONE: | 2:00-Talk E | Jefferson C
| CHOOSE | 2:30-Talk D | Jefferson A
| ONE: | 2:30-Talk F | Jefferson C
3:00-5:00 PM |  | Career & Innovation Fair - Dairy B Contest Teams and Academy students | Anthony Wayne Ballroom AB
Morning Contest and Academy presentation teams are required to attend.
3:00-5:00 PM |  | Corporate Technology Presentations - Dairy A Contest Teams and Academy students | Jefferson A and Jefferson C
Morning Contest and Academy presentation teams are required to attend.
| CHOOSE | 3:00-Talk A | Jefferson A
| ONE: | 3:00-Talk C | Jefferson C
| CHOOSE | 3:30-Talk B | Jefferson A
| ONE: | 3:30-Talk D | Jefferson C
|  | 4:00-Talk E | Jefferson A
|  | 4:30-Talk F | Jefferson A
5:00–6:00 PM |  | Dismantle sponsor booths | Anthony Wayne Ballroom AB
4:30–6:00 PM |  | Judges complete and turn in assessments and rankings, finalize presentation | Dairy Challenge Central, Jefferson B
4:30–6:00 PM |  | Collection of surveys from coaches, sponsors and judges | Dairy Challenge Central, Jefferson B
4:30–6:00 PM |  | Coaches pick up university computers | IT, Board Room
6:15–6:30 PM |  | Judges present their findings to participants | Dairy A: Harrison Meeting Room A | Existing set - may want to add 35 addtl chairs but leave room in back and along sides for standing: anticipate about 80 per room)
Dairy B: Harrison Meeting Room B
Dairy C: Harrison Meeting Room C
Dairy D: Harrison Meeting Room D
18:30 |  | Presentation equipment returned to Dairy Challenge Central | Dairy Challenge Central, Jefferson B
18:30 |  | Contestant social with sponsors | Harrison Foyer | cash bar until 15 minutes after start of dinner
19:30 |  | NAIDC Awards Banquet | Anthony Wayne Ballroom AB | On 14" risers: podium, mic, table for awards. Banquet for 350, large screen, AV cart with electrical access

## Committee Responsibilities
revised 7-25-09
Responsibilities of the Volunteers Subcommittee
PRE CONTEST
Work with Local Host Subcommittee to acquire sufficient contest assistants
Maintain contact list of volunteers
Work with Technology Subcommittee to identify tech support staff for contest
Work with Local Hosts and PR committee to arrange photographers to take candids to be taken at farms
Candids on farms
Team photos on Saturday
Winning teams after banquet
Arrange for a backup camera and/or photographer, just in case
Use list of jobs and assignments to assign volunteers to tasks for the contest
Work with local hosts to be sure job list reflects contest needs
Assign volunteers for pre-contest tours if needed
Assign a Volunteer Coordinator for the contest
This person will lead all Volunteer Meetings and provide instructions
Will also ensure that all tasks have a person assigned to them and manage on-site changes
Work with Executive Director to get RSVP from volunteers for all meals
Provide information to WDE for volunteer packets
List of jobs: copies can be made ahead or on-site by WDE
Responsibilities of dairy visit volunteers
Responsibilities of interview volunteers
Responsibilities of presentation volunteers
POST CONTEST
Thank volunteers
Review contest and suggest changes or improvements for next year

## Volunteer Contact Info
Name |  | Company | Email | Phone | Availability
Kirk | Sattazahn | Select Sires | kirk7@selectsirepower.com | 610-698-4754 Cell | Fri AM, Fri PM
Dave | Whitlock | Select Sires | dwhitloc@swva.net
Jared | Zimmerman | Select Sires
Aaron | Horst | ABS Global | aaron.horst@absglobal.com
Doug | Baker | ABS Global
Brandon | Sowder | ABS Global
Todd | Riggs | ABS Global
Maggie | Hamm | Carolina Farm Credit | bfox@carolinafarmcredit.com
Sarah | Rachels | Carolina Farm Credit
Mitchel | Pridmore | Carolina Farm Credit
Lindsay | Merrill Ellsworth | Carolina Farm Credit
Larry | Swartz | Genex Cooperative Inc.
Johnny | Bonnette | Genex Cooperative Inc. | jbonnette@crinet.com
Lucas | Sjostrom | Hoards Dairyman | lsjostrom@hoards.com
Brad | Fest | Land O' Lakes Purina Feed | rpoeppel@landolakes.com
Stan | Penland | Land O' Lakes Purina Feed
Matt | Budine | Progressive Dairy Solutions, Inc. | mbudine@progressivedairysolutions.com
Norm | Barney | Central Life Sciences | bnorm628@sbcglobal.net
Bradley | Oldick | Southern States Cooperative, Inc. | bradley.oldick@sscoop.com
Anna | Munday | Southern States Cooperative, Inc.
Linda | Davis | Southern States Cooperative, Inc.
Houston | Honeycut | Southern States Cooperative, Inc. | houston.honeycutt@sscoop.com
Mike | Helms | Southern States Cooperative, Inc.
LOCAL
Shannon | Davidson | NC State | sdavids@ncsu.edu
Brinton | Hopkins | NC State | brinton_hopkins@ncsu.edu
Matt | Lange | NC State | mlange@ncdairyadvantage.com
Mike | Roberts | NC State | mtrobert@ncsu.edu
Ken | Vaughn | NC State | ken_vaughn@ncsu.edu
Steve | Washburn | NC State | steve_washburn@ncsu.edu
Michelle | Jones | DRMS | michele_jones@ncsu.edu
Glen | Staebner | VAS | glen@vas.com
Saturday for debriefing (team with a board member) |  |  | E-Mail
Gamaleden | Abdelrahim | Alabama A&M University | gamal.abdrahim@aamu.edu
Dr. Stan | Hendersen | California Polytechnic State University | shenders@calpoly.edu
Jon | Robison | California State University - Fresno | jonr@csufresno.edu
Todd | Webb | Delaware Valley College | todd.webb@delval.edu
Laurie | Rincker | Eastern Kentucky University | laurie.rincker@eku.edu
Dr. Lee | Kilmer | IA State University | lhkilmer@iastate.edu
Mike | Brouk | K State University | mbrouk@ksu.edu
Cathy | Williams | Louisiana State | cwilliams@agcenter.lsu.edu
Dr. Miriam | Weber Nielsen | Michigan State University | msw@msu.edu
Stephanie | Hill Ward | Mississippi State University | srhill@ads.msstate.edu
Gabriella | Varga | Penn State University | gvarga@psu.edu
Dr. Maurice | Eastridge | The Ohio State University | eastridge.1@osu.edu
Masahito | Oba | University of Alberta | moba@ualberta.ca
Albert | DeVries | University of Florida | devries@ufl.edu
Mary | Sowerby | University of Florida | meso@ufl.edu
John | Walton | University of Guelph | jswalton@uoguelph.ca
Amin | Ahmadzadeh | University of Idaho | amin@uidaho.edu
Kate | Cowles | University of Illinois | kcowles2@illinois.edu
David | Marcinkowski | University of Maine | davidmar@maine.edu
Peter | Erickson | University of New Hampshire | peter.erickson@unh.edu
Wanda | Emerich | University of Vermont | emerich@whminer.com
David | Combs | University of Wisconsin-Madison | dkcombs@wisc.edu
Chuck | Steiner | University of Wisconsin-Platteville | steinerc@uwplatt.edu
Dennis | Cooper | University of Wisconsin-River Falls | dennis.p.cooper@uwrf.edu
Mark | Hannigan | Virginia Tech University | mhanigan@vt.edu
John | Swain | Washington State University | swainjb@wsu.edu
Michael | McGilliard | Virginia Tech University | mcg@vt.edu
OTHER
Jake | Anderson | Louisiana State | jande82@tigers.lsu.edu |  | Fri, Sat
Seth | Mizell | Louisiana State | mmizel1@tigers.lsu.edu |  | Fri, Sat

## List of Jobs & Assignments
revised 3/29/11 Shannon Davidson
Complete List of Contest Jobs and Assignments - Revised April 2, 2013 5th Addition
unassigned but available:
Friday
| JOB | NOTES | ASSIGNED PERSON
Registration
| Database | Exec Dir | Molly Kelley
| Assistant |  | Ruth Stampfl, WDE
| Name tags | WDE | Laura Herschleb, WDE
| Coach/Contestant Packets | WDE | Coleen Jones/Dave Winston
| Collect computers 1 | Tech Support AM | Michelle Jones, DRMS
| Collect computers 2 | Tech Support AM | Glen Staebner, VAS
| Collect computers 3 | Tech Support AM | David Nansel, DHI Computing Services, Inc.
| Collect computers 4 | Tech Support AM | Kas Ingawa
| Check in and label computers | Contest assistant | Kas Ingawa
| Allocate Sponsor booth spaces | Fin Chr, local host | Rob Sheffer
Morning Program & Events
| Direct coaches and students | Volunteer | Joanne Knapp, Tom Noyes
| Contest welcome | BOD Chair | Luciene Ribeiro
| Contest overview | BOD Vice Chair | Mike Van Amburgh
| Contest instructions | Program Chair | Dave Winston
| Transportation coordinator | Contest assistant | Tamilee Nennich
| Volunteer meeting | Volunteer Coordinator | Miriam Weber Nielsen/Jim Sipiorski
| Judge Van Driver | Contest assistant | Sarah Burczynski (MSU)
| Judge Van Driver | Contest assistant | Tara Dennis (Purdue)
| Judge Van Driver | Contest assistant | Dianne Shoemaker
| Judge Van Driver | Contest assistant | Bob Albrecht
| Judges meeting | Prog Chr/Judges Facilitr | Dave Winston/Dave Prentice
| Assign team work rooms | Contest Asst/Prog Chr | Ruth Stampfl/Coleen Jones
| Prepare instruction & info sheet | Contest Asst/Prog Chr | Ruth Stampfl/Coleen Jones
| Update & load to cd contestant bios | WDE | Laura Herschleb
| Coaches meeting | BOD Chr, Prog Chr | Luciene Ribeiro, Mike Van Amburgh, other board members available
| Coaches meeting | Exec Dir | Molly Kelley
| Coaches et al tour leader | School Host / BOD | Mike Van Amburgh | * visit all 4 contest farms with coaches to serve as a casual resource about dairying in NC (no prepared comments needed)
| Coaches et al tour leader | School Host / BOD | Marcia Endres | expect to depart in 15 passenger vans at 12 pm on Friday from Hickory Conv. Center,
| Coaches et al tour leader | School Host / BOD | Tamilee Nennich/Miriam Weber Nielsen | expected to return to Hickory Conv. Center by 5 pm
| Dairy A Visit | Purdue Prairie
| Local Industry Rep coordinator |  | Chuck Jamison | *stay for Friday afternoon Academy students
| Dairy visit assistant 1 | Volunteer | Ben Cashell
| Dairy visit assistant 2 | Volunteer | JJ Degan
| Dairy visit assistant 3 | Volunteer | Ted Holthaus
| Dairy visit assistant 4 | Volunteer | Sarah Fraley
| Dairy visit assistant 5 | Volunteer | Glenn Noll
| Dairy visit assistant 6 | Volunteer | Tom Rienholt
| Dairy visit assistant 7 | Volunteer | Preston Vincent
| Dairy visit assistant 8 | Volunteer | Jill Lokai
| Dairy visit assistant 9 | Volunteer | Scott Flowers
| Photographer | coordinate w/ Media Chr | Amanda Smith
| Photo assistant | coordinate w/ Media Chr
| Dairy B Visit | Boilermaker Gold
| Local Industry Rep coordinator |  | Melanie Lynch | *stay for Friday afternoon Academy students
| Dairy visit assistant 1 | Volunteer | Matt Bull
| Dairy visit assistant 2 | Volunteer | Nathan Kuehnert
| Dairy visit assistant 3 | Volunteer | Matt McVey
| Dairy visit assistant 4 | Volunteer | Kevin Ziemba
| Dairy visit assistant 5 | Volunteer | Julie Ziegler
| Dairy visit assistant 6 | Volunteer | Greg Beavers
| Dairy visit assistant 7 | Volunteer | Jeff Hoeger
| Dairy visit assistant 8 | Volunteer | Gabe Papoi
| Dairy viist assistant 9 | Volunteer | Carol Coulombe
| Photographer | coordinate w/ Media Chr | Melissa Hart
| Photo assistant | coordinate w/ Media Chr
| Dairy C Visit | Coldwater
| Local Industry Rep coordinator |  | Jerry Krummrey
| Dairy visit assistant 1 | Volunteer | Laura Weisz
| Dairy visit assistant 2 | Volunteer | Kristi Keilen
| Dairy visit assistant 3 | Volunteer | Jana Mussard
| Dairy visit assistant 4 | Volunteer | Jeremy Higgins
| Dairy visit assistant 5 | Volunteer | Gary Smith
| Dairy visit assistant 6 | Volunteer | Mark Adam
| Dairy visit assistant 7 | Volunteer | Aaron Host
| Dairy visit assistant 8 | Volunteer | Nathan Lippert
| Dairy visit assistant 9 | Volunteer | Robin Starkenburg
| Photographer | coordinate w/ Media Chr | Amy te Plate-Church
| Photo assistant | coordinate w/ Media Chr
| Dairy D Visit | Quincy
| Local Industry Rep coordinator |  | Kathy Lee
| Dairy visit assistant 1 | Volunteer | Jillian Holdwick
| Dairy visit assistant 2 | Volunteer | Laura Zagorski
| Dairy visit assistant 3 | Volunteer | Chris Lahmers
| Dairy visit assistant 4 | Volunteer | Matt Costigan
| Dairy visit assistant 5 | Volunteer | Jess Jakubik
| Dairy visit assistant 6 | Volunteer | Phil Monson
| Dairy visit assistant 7 | Volunteer | Ed Zuchnik
| Dairy visit assistant 8 | Volunteer | Justin Olson
| Dairy visit assistant 9 | Volunteer | Todd Kronberg
| Photographer | coordinate w/ Media Chr | Laura Moser/Alex Schnabelrauch
| Photo assistant | coordinate w/ Media Chr
Afternoon Program & Events
| Lunch Instructions to teams | Program Chair | Dave Winston, Kas Ingawa, Luciene Ribiero
| Hand out computers to teams | Contest assistant | Michelle Jones, DRMS
| Hand out computers to teams | Volunteer | Glen Staebner, VAS
| Judges' lunch w/ dairy managers | Prog Chr/Judges Facilitr | Coleen Jones/Dave Prentice
| Judges meeting | Prog Chr/Judges Facilitr | Coleen Jones/Dave Prentice
| Volunteer meeting | Volunteer Coordinator | Miriam Weber Nielsen/Jim Sipiorski
| Monitor team workrooms | Volunteer | Jim Sipiorski
| Monitor team workrooms | Volunteer | Dave Prentice
| Monitor team workrooms | Volunteer | Kristy Daniels
| Refresh breaks | Need depends on hotel | Tana Dennis, Purdue
| Tech support | Tech Support | Michelle Jones, DRMS
| Tech support | Tech Support | Glen Staebner, VAS
| Tech support | Tech Support | David Nansel, DHI Computing Services, Inc
| Tech support | Tech Support | Kas Ingawa, DRMS
| Allocate sponsor booth spaces | Fin Chr, Industry Host | Owen Bewley
| Greet sponsors | Finance Chair | Owen Bewley
| Greet sponsors | Industry Host | Devin Albrecht
| Greet media/answer questions | Publicity Chr | Amy te-Plate Church
| Dairy 1 Interviews | Stockwell
| Interview moderator | Volunteer | Board member
| Interview timer | Volunteer | Julie Ziegler
| Interview door keeper | Volunteer | Matt Costigan
| Dairy 2 Interviews | Brand
| Interview moderator | Volunteer | Board member
| Interview timer | Volunteer | Gary Smith
| Interview door keeper | Volunteer | Sarah Burczynski
| Dairy 3 Interviews | Preston
| Interview moderator | Volunteer | Board member
| Interview timer | Volunteer | Ben Cashell
| Interview door keeper | Volunteer | Jillian Holdwick
| Dairy 4 Interviews | Bloom
| Interview moderator | Volunteer | Board member
| Interview timer | Volunteer | Matt Bull
| Interview door keeper | Volunteer | Laura Weisz
Collect presentations
| Dairy 1 | Tech Support | Kas Ingawa
| Dairy 2 | Tech Support | Michelle Jones
| Dairy 3 | Tech Support | Glen Staebner
| Dairy 4 | Tech Support | David Nansel
Evening Events
| Prepare copies of presentations | WDE | Laura Herschleb, Molly Kelley
| Collect judges Assessments | Prog Chr/Judge Facilitr | Coleen Jones/Dave Prentice
| Prepare for computer distribution | WDE | Laura Herschleb, Molly Kelley
| Secure Contest Laptops | Program Chr/Exec Dir | Coleen Jones/Kas Ingawa/Molly Kelley
Evening Social Program
| Friday Night Emcee | BOD | Luciene Ribeiro
| Welcome | Host School | Maurice Eastridge
| Introductions | BOD | Mike Van Amburgh
| Instructions | BOD
| Remind Volunteers of Sat AM Mtg | BOD | Miriam Weber Nielsen/Jim Sipiorski
| Develop PPT | coordinate w/ Media Chr | Amy te-Plate Church/Dave Winston
Saturday
| JOB | NOTES | ASSIGNED PERSON
Morning Events
| Check out presentation rooms | Program Chr/Exec Dir | Coleen Jones, Molly Kelley
| Distribute equipment to rooms | School Host/WDE
| Volunteer meeting | Volunteer Coordinator | Miriam Weber Nielsen/Jim Sipiorski
| Judges meeting | Prog Chr/Judge Facilitr | Coleen Jones/Dave Prentice
| Direct set up of sponsor booths | Fin Chr/ Industry Host | Owen Bewley
| Hand out presentations 1 hr before | WDE | Laura Herschleb
| Monitor prep & collect finance data | Volunteer | Tana Dennis
| Monitor prep & collect finance data | Volunteer | Sarah Burczynski
| Photographer | Volunteer | Amy te Plate
| Photographer | Volunteer | Amanda Smith
| Refresh breaks | Depends on Hotel
| Refresh breaks | Depends on Hotel
Dairy 1 Morning Presentations
| Moderator | Volunteer | Board member
| Timer | Volunteer | Gary Smith
| Tech support | Volunteer | Kas Ingawa
| Hall monitor (door monitor) | Volunteer | Jon Townsend
| Debriefing interviewer | BOD | Board member
Dairy 2 Morning Presentations
| Moderator | Volunteer | Board member
| Timer | Volunteer | Gabe Papoi
| Tech support | Volunteer
| Hall monitor | Volunteer | Nathan Kuehnert
| Debriefing interviewer | BOD | Board member
Dairy 3 Morning Presentations
| Moderator | Volunteer | Board member
| Timer | Volunteer | Duane Logan
| Tech support | Volunteer
| Hall monitor | Volunteer | Kevin Ziemba
| Debriefing interviewer | BOD | Board member
Dairy 4 Morning Presentations
| Moderator | Volunteer | Board member
| Timer | Volunteer | Mark Adam
| Tech support | Volunteer
| Hall monitor | Volunteer | Aaron Host
| Debriefing interviewer | BOD | Board member
Afternoon Events
| Volunteer Meeting PM | Volunteer Coordinator | Miriam Weber Nielsen/Jim Sipiorski
| Prepare for certificate printing | WDE/Contest assistant | Laura Herschleb/Ruth Stampfl
| Hand out presentations 1 hr before | WDE | Laura Herschleb
| Monitor prep & collect finance data | Volunteer | Tana Dennis
| Monitor prep & collect finance data | Volunteer | Sarah Burczynski
| Refresh breaks | Depends on Hotel
| Refresh breaks | Depends on Hotel
| Dairy 1 Afternoon Presentations | Adams
| Moderator | Volunteer | Board member
| Timer | Volunteer | Joanne Knapp
| Tech support | Volunteer | Kas Ingawa
| Hall monitor | Volunteer | Tom Noyes
| Debriefing interviewer | BOD | Board member
| Dairy 2 Afternoon Presentations | Bushnell
| Moderator | Volunteer | Board member
| Timer | Volunteer | Melanie Lynch
| Tech support | Volunteer
| Hall monitor | Volunteer | Mark Adam
| Debriefing interviewer | BOD | Board member
| Dairy 3 Afternoon Presentations | Dewitt
| Moderator | Volunteer | Board member
| Timer | Volunteer | Chuck Jamison
| Tech support | Volunteer
| Hall monitor | Volunteer | Duane Logan
| Debriefing interviewer | BOD | Board member
| Dairy 4 Afternoon Presentations | Sacketts
| Moderator | Volunteer | Board member
| Timer | Volunteer | Gary Smith
| Tech support | Volunteer
| Hall monitor | Volunteer | Jill Lokai
| Debriefing interviewer | BOD | Board member
Evening Events
| Collect Sponsor Surveys | Finance Chair | Owen Bewley
| Collect laptops, pointers, timers etc | School Host/WDE | Laura Herschleb/Ruth Stampfl
| Collect Coaches Surveys | Exec Dir | Molly Kelley
| Collect Judge Surveys | Prog Chr/Judge Facilitr | Coleen Jones/Dave Prentice
| Collect results from Judges | Prog Chr/Judge Facilitr | Coleen Jones/Dave Prentice
| Compile Rankings of teams | WDE | Laura Herschleb/Ruth Stampfl/Molly Kelley
| Print award certificates | WDE | Laura Herschleb/Ruth Stampfl/Molly Kelley
| Prepare Team results packets/cds | WDE | Laura Herschleb/Ruth Stampfl/Molly Kelley
| Prepare Judges results packets/cds | WDE | Laura Herschleb/Ruth Stampfl/Molly Kelley
| Deliver Judges and Team Packets/cds | WDE | Laura Herschleb/Ruth Stampfl/Molly Kelley
Banquet Program
| Prepare PPT pres for Banquet | PR Committee | Amy te-Plate Church/ Dave Winston
| Banquet Emcee | President | Luciene Ribeiro
| Invocation | BOD | Marcia Endres??
| Introduce Sponsors | Finance Chr | Owen Bewley
| Introduce Host Dairies | School Host | Maurice Eastridge, Mike Schutz, Miriam Weber-Nielsen
| Introduce Host School Officials | President | Luciene Ribeiro
| Introduce Volunteers & Judges | Program Chr | Coleen Jones/Dave Prentice
| Announce Awards | BOD | Devin Albrecht/Chris Dei/Amy te-Plate Church/Jean Conklin

## Volunteer Mtgs
revised 2-23-11
Agendas for Volunteer Meetings during the Contest
FARM VISIT INSTRUCTIONS
Distribute sponsor folders/namebadges to anyone who doesn't have one
Distribute Friday Volunteer Handouts
Review farm visit schedule
Review responsibilities of each person on the visit
Review safety issues
Collect signed participation waivers from all volunteers
Answer any questions
INTERVIEW INSTRUCTIONS
Distribute sponsor folders/namebadges to anyone who doesn't have one
Distribute Friday Volunteer Handout to any people that do not have it
Review responsibilities of each volunteer
Explain job of afternoon monitors - walk in the rooms, observe, see if teams need anything
Distribute stop watches to timers
Answer any questions
MORNING PRESENTATIONS
Provide moderator with presentation copies for each AM team
1 for moderator, 5 for judges, 1 for dairy manager/owner
Ensure all volunteers have a Saturday packet (assignments, responsibilities, & schedules)
Review responsibilities of each volunteer
Be sure that moderators are aware of the judges' responsibilities
Provide a list of team names and numbers in presentation order to lead videographer
Answer any questions
AFTERNOON PRESENTATIONS
Provide moderator with presentation copies for each PM team
1 for moderator, 5 for judges, 1 for dairy manager/owner
Ensure all volunteers have a Saturday packet (assignments, responsibilities, & schedules)
Review responsibilities of each volunteer
Check videographer has correct list of team names and numbers in presentation order
Answer any questions

## Dairy Visit Volunteers
revised 7-25-09
Responsibilities of Dairy Visit Volunteers |  |  | Friday Morning
ALL dairy visit volunteers should sign liability waiver
Board of Director Dairy Coordinator
Attend dairy visit volunteers meeting
Before the Visit
Receive plastic boots, garbage bags, handi-wipes, farm directions, portable speaker
Ensure that bus driver has received a copy of directions
Get several tape measures from volunteer coordinator
Ensure all teams are on the bus in time for departure to dairy
Accompany students on the bus, hand out boots during the trip to the dairy
Explain timeline for dairy visit, address visit of second facility if needed
During the Visit
Answer general questions from students
Students are not allowed to ask any questions of the farmer or employees
Ensure safety of students - no one allowed at face of bunk silo,
note locations of bulls on farms (announced when doing welcome by farm mgr)
Group Interviews
MODERATE group interview of dairy owner/manager.
Ensure all teams & judges return to the interview area on time
Ensure all teams have equal opportunity to ask questions & use loudspeaker
End interview after 25 minutes
End of Visit
Help to collect plastic boots in garbage bags (provided)
Facilitate loading of teams onto the bus
Collect tape measures from teams and return them to Ruth Stampfl, WDE
Local Industry Representative
Before the Visit
Arrive at the dairy 30 minutes before students.
Decide where to park the bus and have greeting session
Check with manager to see if any areas are off-limits to students.
Pens with bulls, biosecure areas, etc
Check with manager to see if there is a preferred traffic pattern for the visit.
(for example, look at the calves first, visit the hospital last, etc.)
Remind the manager that neither he nor employees are to answer student questions
individually (only during the group sessions).
Refer all questions to dairy visit volunteers during walk through.
Identify locations around the dairy for assistants to answer questions.
Work with Board of Director Coordinator to spread assistants around dairy.
An assistant in parlor area and one at bunker silos to keep students from getting too close
Others at calf rearing, hospital, main barn, feed formulation, etc
During the Visit
Introduce dairy manager(s) to give a welcome and brief overview of the dairy.
Use the loudspeaker and make sure the manager uses it.
If there are any areas off-limits or preferred traffic patterns, announce these to students.
Review safety issues: avoid bunker face, announce where bulls are, etc.
Remind teams they are not to ask any questions of the manager or employees.
Introduce dairy visit assistants that can answer general questions from students.
Answer general questions from students.
The judge's panel should arrive at the farm at the same time.
Group Interviews
Ensure all teams & judges return to the interview area on time.
End of Visit
Help to collect plastic boots in garbage bags (provided).
Remind the dairy manager about leaving for lunch and interviews
Dairy Visit Assistants
Attend dairy visit volunteers meeting
Before the Visit
Help load all teams on the bus in time for departure.
Accompany students on the bus, hand out boots during the trip to the dairy.
During the Visit
Answer general questions from students.
Students are not allowed to ask any questions of the manager or employees.
End of Visit
Collect plastic boots in garbage bags (provided).
Help to get students loaded on bus promptly.
Dairy Photographer
Attend dairy visit volunteers meeting
Take at least one "action" shot of each team.
Identify at least the school of students in each photo.
Photos to be used for a Power Point presentation during social gatherings
Dairy Photo Assistant
Attend dairy visit volunteers meeting
Write a chronological list of photos taken by the photographer.
Assist in identifying students' school.
** do safety announcements at the farm

## Interview Volunteers
revised 7-25-09
Responsibilities of Interview Volunteers |  |  | Friday Afternoon
NO sponsors allowed to sit in
NO coaches allowed to sit in
Schedule
1:30 p.m. | Attend volunteer meeting
1:45 p.m. | Set up rooms with producer on one side of table, students on the other; others to the sides
2:00 p.m. | First interview, continue on 15-minute intervals
4:00 p.m. | Clean up rooms, return any equipment to the NAIDC administrative office
Responsibilities
Moderator
Coordinate interviews
Instruct students that they will have 12 minutes, and will get a 2-min warning
Facilitate Q&A between teams and producers
Determine validity of each question; and give quick reason why a question is not allowed
Instruct dairy manager not to answer inappropriate questions
See examples below to help guide your decisions
Timer
12 minutes per team for interview
Give hand signal for 2-minute warning
End session after 12 minutes
If teams are late, they lose the time
Door Keeper
Remain outside interview room
Coordinate team entry into room on time
Teams are scheduled at 15-minute intervals
Coordinate team movement between working rooms and interview room
Judges (2)
Observe team strategies and questions asked
Examples of Appropriate and Inappropriate Questions
Invalid | How much overcrowding do you have in pen one?
Allowed | What is your definition of over-stocking?
Invalid | What is your biggest metabolic problem?
Allowed | The number of ketosis cases in your database indicate a big problem; is that correct data?
Invalid | What is your biggest reproductive problem?
Allowed | The data shows that your cows average 120 days open; is that a correct value?
Invalid | How much do your cows eat in one day?
Allowed | Do you weigh the feed provided and feed that is refused daily?
it would be good to check with people who have served as moderator to be sure we're providing good examples here

## Presentation Volunteers
revised 7-25-09
Responsibilities of Presentation Volunteers |  |  | Saturday
For timer and door monitor volunteers: An individual has been assigned to fill each of these responsibilities for the AM session and the PM session.
If you would like to coordinate with the person serving in your room and your position (i.e., AM timer and PM timer Dairy A, AM monitor and PM monitor Dairy B, etc.),
then the two of you may work together to switch off to fill the position throughout the day instead of one working all morning and one working all afternoon.
Schedule
7:00 a.m. | Brief organizational meeting for morning volunteers
7:30 a.m. | Set up presentation rooms
7:45 a.m. | First morning presentation, Continue at 60-minute intervals
11:45 a.m. | Lunch break (lunches provided)
12:00 p.m. | Brief organizational meeting for afternoon volunteers
12:30 p.m. | First afternoon presentation, Continue at 60-minute intervals
4:35 p.m. | Clean up presentation rooms
Responsibilities
Moderator
In control of the presentation room
Coordinate all presentation activities and maintain allocated time schedule
Provide presentation photocopies to judges & yourself
Seat dairy manager/owner & provide copy of presentations
Provide instructions to teams after they enter the room
Remind teams to stand by podium with mic when talking
Remind teams of videotaping
Remind teams of hand signals at 5 min and 2 min remaining
Remind everyone in room to turn off cell phones
Introduce team by number
If necessary, stop the presentation if too long
Instruct team to have photo taken immediately after question sessions
Have judges introduce themselves during the oral feedback period
Timer
20 minute maximum for presentation
Give teams hand signals at 5 min and 2 min remaining
10 minutes for question period
15 minutes for judges' deliberations
10 minutes for oral feedback
Tech support
Set up computer and projector
Open presentations on laptop
Explain laser pointer and LCD projector controls
Provide technology support as needed
Stenographer w/laptop
Take notes during judges' oral feedback session
Notes to be used as base document for judges' comments to team
Type up final notes of judges panel to give to teams
Door monitor
Remain inside presentation room
No one should enter or leave during presentations and questions
Coordinate team movement between prep rooms and presentation room
Coordinate seating of the team coach(es) - coaches can view their team only
Coordinate movement of sponsors into rooms
Coordinate team entry into room on time
BOD debriefers will pick up teams for debriefing
post sign outside door: presentation in progress - do not enter.
Videographer
Tape presentation and question sessions only
Have microphones for presenters and judges panel
Make sure school name is prerecorded prior to presentation for insertion to video
Make sure the appropriate PPT presentation preloaded on camera is working in sync

## Vol Liability Waiver
North American Intercollegiate Dairy Challenge, April 4 - 6 — Fort Wayne, Indiana
Hosted by Michigan State University, Ohio State University & Purdue University
Host Coordinator ……………………………………………Dr. Maurice Eastridge, eastridge.1@osu.edu
Registration ………………………………………………… Laura Herschleb, WDE Mgmt., PH: 608/224-0400, FX: 608/224-0300, lherschleb@wdexpo.com
Volunteer Release Waiver and Release of Liability
In consideration of the North American Intercollegiate Dairy Challenge furnishing services and/or equipment to enable me to participate in the North American Intercollegiate Dairy Challenge activities, I, the undersigned, agree as follows:
Participation Release
I, on behalf of myself, heirs, executors and administrators, agree to indemnify and hold harmless the North American Intercollegiate Dairy Challenge, and its Board of Directors, agents, officers, volunteers, sponsors, and employees, as well as the Western Regional Committee in Visalia, CA, the community of the Host and the Host Farms, from all liability, loss and expense, including, but not limited to damages, legal expenses and cost of defense, in any matter arising during or from the participation in the North American Intercollegiate Dairy Challenge.
Waiver and Release of Liability
I, on behalf of myself, heirs, executors and administrators, voluntarily assume all risk of accident, injury, or damage and release and forever discharge North American Intercollegiate Dairy Challenge, its Board of Directors, agents, officers, volunteers, sponsors, and employees, as well as the Host School, community of the Host School and Host Farms, from any and all liability for personal injury or property damage of any kind sustained in association with or during participating in the activities, regardless of whether such personal injury or property damage is caused by the negligence of the North American Intercollegiate Dairy Challenge, or its Board of Directors, agents, officers, volunteers, sponsors, and employees, as well as the Host School, community of the Host School, Host Farms, or otherwise.
I HAVE READ THE ABOVE WAIVER AND RELEASE AND BY SIGNING IT AGREE IT IS MY INTENTION TO EXEMPT AND RELIEVE NORTH AMERICAN INTERCOLLEGIATE DAIRY CHALLENGE FROM LIABILITY FOR PERSONAL INJURY, PROPERTY DAMAGE OR WRONGFUL DEATH CAUSED BY NEGLIGENCE OR ANY OTHER CAUSE.
Volunteer Signature | Date
Volunteer Name (Please Print Clearly)
Company Name (Please Print Clearly)

## Photo Authorization
North American Intercollegiate Dairy Challenge, April 4 - 6 — Fort Wayne, Indiana
Hosted by Michigan State University, Ohio State University & Purdue University
Host Coordinator ……………………………………………Dr. Maurice Eastridge, eastridge.1@osu.edu
Registration ………………………………………………… Laura Herschleb, WDE Mgmt., PH: 608/224-0400, FX: 608/224-0300, lherschleb@wdexpo.com
Photo and Video Authorization
Photo and Video Release
Throughout the contest, pictures and videos will be taken of contest activities. Photos and news releases may be sent to the media (newspaper, radio, television and the internet) or used in informational brochures or videos by Lakeshore Technical College and/or North American Intercollegiate Dairy Challenge.
It is the right of the individual whether or not to consent to the use of his/her photos and/or videos.
Photo and Video Authorization
I HAVE READ THE ABOVE AND HEREBY AUTHORIZE NORTH AMERICAN INTERCOLLEGIATE DAIRY CHALLENGE AND/OR LAKESHORE TECHNICAL COLLEGE TO USE ANY PHOTOS OR VIDEOS TAKEN OF ME DURING MIDWEST REGIONAL DAIRY CHALLENGE ACTIVITIES.
Volunteer Signature Date
Volunteer Name (Please Print Clearly)
Company Name (Please Print Clearly)